8/15/22 Planning Commission Minutes

Present: Jim Schweithelm, Michael Gray, Jayne Nold-Laurendeau, Lizzy Higgins

6:10 Meeting opened

6:11 Went over minutes from previous meeting

6:13 Went over draft for cover letter for village center designation.

6:26 Went over draft of map for village center designation.  Discussed possibly adding more detail and sending the draft to Richard Amore for his opinion.

6:36 Reviewed waste water feasibility study progress.  Reviewed draft of postcard intended to involve village property owners in the discussion.  Reviewed list of property owner names and addresses.  Lizzy H will visit the town office to update the property owner list as closely as possible.

7:07 Discussed a plan for outreach to property owners as well as other town residents to involve any interested parties in this discussion.  Came up with a timeline.  Current plan is to hold a public meeting to discuss interest in a feasibility study on Oct 3 at 6:00 pm at the town hall.  Michael G will invite Lynette Claudon from DEC to join in and hopefully present info at this meeting.  Timeline to notify residents about this meeting is as follows:

By 8/28/22 Announcements will be posted on FPF as well as in the other places that warn of town business.

By 8/26/22 postcards will go out to village center land owners.

By 9/9/22 the PC members will follow up either via phone or by visit to the village center landowners if there is no response from the postcard.

9/9/22 at the next PC meeting the PC will prepare for the town wide discussion on Oct 3.

8:02 Discussed plan to prep for public hearing at next meeting as well as look over implementation progress on other issues from the town plan.

8:08 Adjourn